# AI Assisted Two Developer Resourcing and Delivery Plan

Training Assessment Tracker V2 | 80/20 responsibility and resourcing update

| To | Project owner | Date | 23 October 2026 |
| --- | --- | --- | --- |
| From | Planning update | Status | Provisional; unvalidated |
| Decision Requested | Confirm the 80/20 weekly allocation and responsibility model | Prior estimate | 640h; superseded; AI included |
| Planning scope | Build and local acceptance only | Start date | To be agreed |

# 1.   Executive Summary, Recommendation, and Decision Requested

Recommendation: commit 12 project hours each week using the 80/20 allocation below. Keep the provisional target of 3-5 M0-M7 work packages reaching local acceptance each week, subject to a mandatory reforecast after week one. This implies about 2-3 weeks from an agreed kickoff for AI-assisted building and local acceptance only.

| Target cadence | Build duration | Development/design / week | Coordination / week | Total / week |
| --- | --- | --- | --- | --- |
| 3-5 milestones | 2-3 weeks | 10h 06m combined | 1h 54m combined | 12h combined |

## Weekly person-level commitment

| Person | Development or design / week | Coordination and total / week | Feature responsibilities |
| --- | --- | --- | --- |
| Bernie | 8h 06m core development, technical checks and self-review | 1h 30m coordination; 9h 36m total (80%) | Core application, technical verification and documented technical self-review |
| Saturnino | 2h flexible UI design and small UI implementation, including usability and accessibility checks | 24m coordination; 2h 24m total (20%) | Implementation-ready UX design and bounded UI coding after stable contracts |
| Combined | 10h 06m | 1h 54m coordination; 12h total | Coordinated delivery, technical self-review, UX review and owner acceptance |
| Former plan | 12h/person implementation | 3h/person coordination; 15h/person total | Superseded baseline; actual availability unverified |

## Capacity fit and estimate basis

The project requires 12 hours each week: Bernie 9h 36m and Saturnino 2h 24m. Whether these hours fit within current calendars or require changes to other commitments has not been verified and must be confirmed before dates are set.

The superseded 640-hour estimate (328h Dev A; 312h Dev B) already included AI assistance. The revised short forecast is provisional, unvalidated and not apportioned across milestones. Across 2-3 weeks, it totals 24-36 project hours: 20h 12m-30h 18m development/design and 3h 48m-5h 42m coordination. Bernie contributes 19h 12m-28h 48m; Saturnino contributes 4h 48m-7h 12m. These are planning figures, not actual time or proof of completion.

# 2.   Parallel Feature Ownership

Bernie owns core application delivery, technical verification and documented technical self-review. Saturnino consumes stable interfaces, supplies UX and accessibility review, and may implement bounded UI slices after the relevant contract is stable. The project owner provides final product acceptance.

## Bernie | Developer A, core application and technical delivery

Own client/team/member structure, permissions, migrations, domain services, Cerebru integration, assessment and plan logic, reporting data, chatbot security, queues, operations, functional checks, regression coverage and documented technical self-review.

## Saturnino | Developer B, UI and Design

Own user flows, annotated screens, interaction states, responsive and accessible behaviour, design handoffs, and small approved Blade, Livewire, CSS or UI slices that do not alter shared schemas, policies or backend contracts. Review UX and accessibility only; this is not independent technical approval.

## Feature split across M0-M7

M0-M2: Bernie reconciles code, requirements and decisions, then owns client boundaries, permissions, migrations, identity, directory and Cerebru adapters. Saturnino inventories journeys, prepares UX acceptance flows, and designs or implements bounded client/member, branding, import-preview, status and conflict interfaces.

M3-M4: Bernie owns assessment lifecycle, scoring, approvals, calendar, capacity, generation and plan-approval rules. Saturnino designs and may implement assignment, response, review, plan-editor, member-view and workload interfaces after the relevant contracts are stable.

M5-M6: Bernie owns weekly progress services, notes, metrics, exports, access controls, authorised chatbot context, provider controls and retention. Saturnino handles dashboards, charts, reporting, chat, citations and error-state interfaces, including usability and accessibility checks.

M7: Bernie owns technical qualification and operational readiness. Saturnino supports usability review, pilot-facing designs and feedback capture. The project owner accepts locally completed outcomes. Live integration, pilot observation and production release gates remain separate.

# 3.   Delivery Cadence and Local Acceptance

The target treats the eight M0-M7 milestones as work packages for AI-assisted build and local acceptance, not as proof that external or live acceptance gates have passed. Schedule exact items by dependency; no calendar dates are assigned until kickoff. The 80/20 allocation stays constant through weeks 1 and 2 and, if needed, week 3. Saturnino's two delivery hours remain flexible between design and bounded UI implementation according to milestone priority. Work after local acceptance needs a separate forecast.

| Window | Milestone target | Parallel working model | Checkpoint |
| --- | --- | --- | --- |
| Week 1 | 3-5 selected M0-M7 work packages | Bernie leads core delivery; Saturnino works on priority UX and bounded UI after stable contracts | Count local acceptance; record checks, UX findings, hours and blockers |
| Week 2 | 3-5 remaining work packages | Continue core delivery and priority UI; integrate only against stable contracts | Record accepted, blocked and remaining items |
| Week 3, if needed | Overflow, fixes and local acceptance | Use only for spillover; maintain the same 80/20 allocation | Reforecast; do not count live gates as complete |

## End-of-week-one checkpoint

Review the number of work packages that met local acceptance, Bernie's technical self-review and check evidence, any applicable Saturnino UX review, project-owner acceptance, actual hours used, dependency blockers and conflicts with other commitments. Reforecast before continuing, including when fewer than three work packages have local acceptance evidence or a critical dependency blocks the target.

# 4.   Estimate Boundaries, Dependencies, and Release Gates

| Planning item | Current basis | Treatment | Responsible person | Review point |
| --- | --- | --- | --- | --- |
| AI build target | 3-5 work packages/week; 2-3 weeks | Provisional and unvalidated | Bernie + Saturnino within assigned lanes | End of week one |
| Prior estimate | 640 implementation hours; AI included | Superseded baseline; not actuals | Plan maintainer | Retain for history |
| Weekly capacity | Bernie 9h 36m; Saturnino 2h 24m | 12 combined hours/week; calendar fit still to be confirmed | Project owner | Before kickoff |
| Feature dependencies | Decisions, contracts and M0-M7 acceptance criteria | Sequence dependent work; parallelise independent lanes | Bernie owns contracts; Saturnino consumes them for UI work | Weekly coordination and week-one reforecast |
| External release gates | Live identity/Cerebru, AI/SMTP, human pilot, 30-day observation, production | Outside 2-3-week build forecast | Project owner and separately approved reviewers | Separate M7 forecast |

## Scope boundary

The 2-3-week target includes development/design and local acceptance only. Live identity and Cerebru integration, live AI or SMTP qualification, pilot observation, the representative 30-day learning cycle and production deployment/release are excluded and need their own schedule and approvals. Existing CI and application checks remain required evidence. No additional reviewer, paid service, licence, subscription, infrastructure or live-service access is allocated by this planning target.

Planning sources: current M0-M7 charters, the detailed Markdown implementation plan, and the approved 80/20 responsibility model effective 23 October 2026. The original Word implementation plan remains unchanged as the historical baseline.